## Gantt Chart
ComicCraft — Project Gantt Chart (indicative 8-week plan)
ComicCraft – AI Comic Story Creator Using Gemini Models · Timeline reconstructed from implemented module scope (repository history is a single squashed commit)
WBS | Task | Owner/Module | Start | End | Days | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8
1.1 | Extract requirements from supplied design | PROJECT_ANALYSIS.md | 2026-07-01 | 2026-07-07 | 7
1.2 | Define schemas, limits and provider contracts | app/schemas.py; app/config.py | 2026-07-01 | 2026-07-07 | 7
2.1 | FastAPI app factory, routing, middleware, error pages | app/main.py; app/routes.py | 2026-07-01 | 2026-07-14 | 14
2.2 | Templates + static frontend shell | app/templates/*; app/static/* | 2026-07-01 | 2026-07-14 | 14
3.1 | DemoStoryProvider (offline writer) | app/services/llm.py | 2026-07-08 | 2026-07-14 | 7
3.2 | Gemini outline+script stages, JSON validation | app/services/llm.py | 2026-07-08 | 2026-07-14 | 7
3.3 | Retry/backoff jitter + model fallback + demo fallback | app/services/llm.py | 2026-07-08 | 2026-07-21 | 14
4.1 | PlaceholderImageProvider (Pillow art) | app/services/images.py | 2026-07-15 | 2026-07-21 | 7
4.2 | HuggingFaceImageProvider (hosted SDXL) | app/services/images.py | 2026-07-15 | 2026-07-21 | 7
4.3 | DiffusersImageProvider lazy local SD + seeds + fallback | app/services/images.py | 2026-07-15 | 2026-07-28 | 14
5.1 | ComicService orchestration + ProviderInfo | app/services/comic_service.py | 2026-07-22 | 2026-07-28 | 7
5.2 | ComicRepository: UUID workspaces, atomic manifest | app/services/repository.py | 2026-07-22 | 2026-07-28 | 7
6.1 | PDF service: cover + panel pages | app/services/pdf_service.py | 2026-07-22 | 2026-08-04 | 14
6.2 | Download/export-success routes + pages | app/routes.py; templates | 2026-07-29 | 2026-08-04 | 7
7.1 | Responsive CSS breakpoints, loading overlay UX | styles.css; app.js | 2026-07-29 | 2026-08-04 | 7
8.1 | Versioned JSON API + legacy alias + health + test-image | app/routes.py | 2026-07-29 | 2026-08-04 | 7
9.1 | pytest fixtures + API/web/health tests | tests/* | 2026-08-05 | 2026-08-11 | 7
9.2 | Service-level tests (retry, model switch, demo story) | tests/test_story_service.py | 2026-08-05 | 2026-08-11 | 7
9.3 | Manual verification: end-to-end run, PDF, fallbacks | — (evidence in Phase 6) | 2026-08-05 | 2026-08-11 | 7
10.1 | Docker + compose + non-root healthcheck | Dockerfile; docker-compose.yml | 2026-08-12 | 2026-08-18 | 7
10.2 | OS + Android setup/run scripts; cleanup utility | *.sh/*.bat; scripts/cleanup.py | 2026-08-12 | 2026-08-18 | 7
11.1 | README / QUICKSTART / ANDROID-SPCK documentation | *.md | 2026-08-12 | 2026-08-25 | 14
11.2 | Academic 8-phase documentation package | ComicCraft_Phase_Wise_Submission/ | 2026-08-19 | 2026-08-25 | 7
11.3 | Presentation + viva preparation | 08_Project_Demonstration/ | 2026-08-19 | 2026-08-25 | 7
Milestones (definition of done — evidence in Phase 6)
ID | Milestone & evidence | Week
M1 | App boots — GET /health returns ok with resolved demo/placeholder modes | W1
M2 | End-to-end comic — POST /api/v1/comics → 201, panels+pdf+manifest on disk | W4
M3 | PDF export — GET /download/{id} → application/pdf (%PDF header) | W5
M4 | Preview & reopen — /comics/{id} re-renders from manifest | W5
M5 | Fallback proven — Story+image fallbacks produce flagged output | W6
M6 | Test suite green — 11 tests pass offline; coverage 80% | W6
M7 | Deployable package — Dockerfile + compose + scripts complete | W7
M8 | Docs complete — 8-phase academic package delivered | W8
| Legend: | Multi-week task | Single-week task