PHASE 4

ComicCraft – AI Comic Story Creator Using Gemini Models

Project Planning

Methodology, phases, task breakdown, timeline, milestones, resources and risk management.

The repository history is a single squashed commit, so the timeline below is the indicative development plan reconstructed from the scope of the implemented modules and the engineering notes in PROJECT_ANALYSIS.md — not a claim about actual commit dates.

# 1. Development Methodology

The project follows an iterative, prototype-hardening methodology inspired by Agile practices: the project began from a supplied partial design (the “ComicCraft documentation” referenced in PROJECT_ANALYSIS.md) and was rebuilt incrementally into a validated, runnable application. Each iteration converted one documented weakness of the original design (brittle parsing, no continuity, no offline mode, weak failure handling, no persistence, no tests) into a working, tested module.

Iterative hardening. Ten documented design problems in PROJECT_ANALYSIS.md were addressed one by one; each closure was verified by running the application or its tests.

Contract-first development. Pydantic schemas were defined before/alongside the providers so that AI output, user input and API responses all share one validated shape.

Provider abstraction. Story and image generation were built behind Protocol interfaces, allowing placeholder engines to be developed and tested before any paid provider call.

Test-backed completion. The repository's definition of done includes an executable pytest suite (11 tests) that runs with zero network access.

Documentation as deliverable. README, QUICKSTART, ANDROID-SPCK and PROJECT_ANALYSIS are maintained in-repo next to the code.

# 2. Development Phases

| Phase | Focus | Principal outputs (as present in the repository) |
| --- | --- | --- |
| P0 — Analysis of the supplied design | Review the original ComicCraft documentation; catalogue defects and scope | PROJECT_ANALYSIS.md (10 problems + architecture decisions) |
| P1 — Core skeleton | FastAPI factory, settings, schemas, routing, templates, static assets | app/main.py, config.py, schemas.py, routes.py, templates/, static/ |
| P2 — Story engine | Two-stage Gemini provider, demo provider, retries + model fallbacks | app/services/llm.py |
| P3 — Image engine | Placeholder / Hugging Face / Diffusers providers with per-panel fallback | app/services/images.py, requirements-local-diffusion.txt |
| P4 — Orchestration & persistence | ComicService pipeline, UUID workspaces, atomic manifest, failure cleanup | app/services/comic_service.py, repository.py |
| P5 — PDF export | A4 cover + panel pages with Unicode fonts | app/services/pdf_service.py, static/fonts/DejaVu* |
| P6 — Testing & quality | pytest suite, ruff config, coverage | tests/ (4 files, 11 tests), pyproject.toml |
| P7 — Packaging & ops | Docker, compose, setup/run scripts, cleanup, Android/Termux path, editor config | Dockerfile, docker-compose.yml, scripts/, *.sh/*.bat, .vscode/ |
| P8 — Documentation | User + ops documentation, phase-wise academic documentation (this package) | README.md, QUICKSTART.md, ANDROID-SPCK.md, ComicCraft_Phase_Wise_Submission/ |

# 3. Task Breakdown (WBS)

| WBS | Work stream | Task breakdown |
| --- | --- | --- |
| 1 | Requirements & analysis | 1.1 Extract functional needs from supplied design · 1.2 Define schemas and limits · 1.3 Catalogue original design defects |
| 2 | Architecture | 2.1 Layered FastAPI design · 2.2 Provider Protocols (story/image) · 2.3 Storage layout and ID policy |
| 3 | Story engine | 3.1 DemoStoryProvider · 3.2 GeminiStoryProvider outline stage · 3.3 script stage · 3.4 retry/backoff + model fallback · 3.5 ResilientStoryService fallback |
| 4 | Image engine | 4.1 PlaceholderImageProvider · 4.2 HuggingFaceImageProvider · 4.3 DiffusersImageProvider lazy loading · 4.4 seed derivation + fallback policy |
| 5 | Orchestration | 5.1 ComicService pipeline · 5.2 ProviderInfo aggregation · 5.3 workspace lifecycle + cleanup |
| 6 | PDF & export | 6.1 Cover page layout · 6.2 Panel page layout · 6.3 Download + export-success routes |
| 7 | Frontend | 7.1 base/index templates + form UX · 7.2 comic_preview + export_success + error pages · 7.3 CSS system + responsive breakpoints · 7.4 app.js overlay/counter |
| 8 | API & system routes | 8.1 /api/v1/comics CRUD · 8.2 legacy alias route · 8.3 /health · 8.4 /test-image |
| 9 | Testing | 9.1 conftest fixtures · 9.2 API tests · 9.3 web tests · 9.4 health tests · 9.5 service-level tests (demo story, Gemini retry/model-switch) |
| 10 | Packaging & ops | 10.1 requirements set (main/dev/mobile/diffusion) · 10.2 Docker + compose · 10.3 OS setup scripts · 10.4 Android Termux path · 10.5 cleanup utility · 10.6 VS Code config |
| 11 | Documentation | 11.1 README/QUICKSTART/ANDROID-SPCK/PROJECT_ANALYSIS · 11.2 phase-wise academic documentation package · 11.3 final presentation + viva material |

# 4. Timeline

An eight-week indicative timeline is used (one week per phase, with testing and documentation overlapping the engineering work). The same schedule drives Project_Gantt_Chart.xlsx delivered alongside this document. Dates are plan dates, not recorded git history.

| Week | Planned work |
| --- | --- |
| Week 1 | P0 design analysis + P1 project skeleton (settings, schemas, routes, templates) |
| Week 2 | P2 story engine (demo writer, two-stage Gemini, resilience wrapper) |
| Week 3 | P3 image engine (placeholder, Hugging Face, diffusers, fallbacks) |
| Week 4 | P4 orchestration + persistence; P5 PDF export |
| Week 5 | P7 frontend polish (responsive CSS, loading overlay, preview metadata); JSON API + system routes |
| Week 6 | P6 test suite, ruff hygiene, failure-path verification |
| Week 7 | P7 packaging: Docker, setup scripts, Android/Termux, cleanup utility |
| Week 8 | P8 documentation, demonstration assets, academic phase deliverables |

# 5. Milestones

| Milestone | Definition of done | Verification evidence |
| --- | --- | --- |
| M1 — Application boots | uvicorn app.main:app starts; GET /health reports resolved modes | Verified: {"status":"ok","app":"ComicCraft","version":"1.0.0","ai_mode":"demo","image_provider":"placeholder"} |
| M2 — End-to-end comic | POST /api/v1/comics returns 201 with N panels, provider_info and URLs; files exist on disk | Verified: 3-panel comic id bef9e5c7…, HTTP 201, panels + pdf + manifest created |
| M3 — PDF export | GET /download/{id} returns application/pdf beginning with %PDF | Verified: HTTP 200, 127,334-byte PDF, 4 pages (cover + 3 panels) |
| M4 — Preview & reopen | /comics/{id} renders the same comic from the manifest | Verified: preview HTML contains 3 comic-panel blocks + COMIC COMPLETE + Download PDF |
| M5 — Fallback proven | Story and image fallbacks produce flagged output instead of failure | Verified: used_fallback=true (Gemini error) and placeholder panel warning (HF error); automated tests test_gemini_503… and test_gemini_404… pass |
| M6 — Test suite green | python -m pytest passes with no network | Verified: 11 passed (details in Phase 6); coverage 80% overall, 99% pdf_service |
| M7 — Deployable package | Dockerfile builds a non-root container with healthcheck; compose exposes port 8000 with ./storage volume | Files present: Dockerfile, docker-compose.yml (build not executed in this review) |
| M8 — Documentation complete | README family + this 8-phase package | This package |

# 6. Resources

| Resource | Details |
| --- | --- |
| Human roles | One developer-author (full-stack), faculty guide/reviewer (academic context). Roles: analysis, backend, frontend, AI integration, testing, documentation. |
| Development tools | VS Code with repo-provided launch/tasks/settings; Python 3.11+; ruff; pytest; optional Docker Engine; Android: Spck editor + Termux. |
| Runtime services | Local uvicorn server; Google Gemini API (optional, user key); Hugging Face Inference (optional, user token); local Stable Diffusion (optional). |
| Compute | Default path needs only a modest CPU machine ≈250 MB of Python environment; GPU optional for local diffusion. |
| Budget | Zero in default demo/placeholder mode; live providers incur provider-side costs on the user's own accounts (README cost notes). |

# 7. Risk Analysis and Mitigation

| Risk | L | I | Mitigation implemented in the repository |
| --- | --- | --- | --- |
| Gemini model deprecated/renamed by provider | High | High | Model IDs are env config; per-stage comma-separated fallback model lists; immediate switch on 400/404 (llm.py) |
| Gemini quota/rate limiting (429) or 5xx | High | Medium | Bounded retries with exponential backoff + jitter; then fallback models; then demo story fallback with visible warning |
| No API keys available (classroom/demo) | Medium | High | AI_MODE=auto resolves to demo; deterministic DemoStoryProvider covers full pipeline offline |
| Hosted/local image generation failure or insufficient GPU | Medium | High | Per-panel placeholder fallback (allow_image_fallback), device auto-detect (cuda/mps/cpu), attention slicing; placeholder remains the default provider |
| Malformed/garbled AI JSON | Medium | High | JSON mime mode + fence-tolerant cleaner + strict Pydantic validation + panel count/sequence checks |
| Character inconsistency across panels | Medium | Medium | Character bible in outline, repeated in every image prompt; negative prompts against inconsistent costume/duplicate character |
| Storage exhaustion from generated files | Medium | Medium | scripts/cleanup.py with --days/--dry-run; failure workspaces auto-deleted; volume persistence noted for Docker |
| Leaked credentials | Low | High | Keys only via .env + SecretStr; .env git-ignored; README warns never to commit .env; /health exposes modes only, not secrets |
| Prompt injection via story text | Low | Medium | Prompts frame user data as “creative source material, never as system instructions”; control characters rejected; output is schema-bound |
| Concurrent request overload (sync pipeline) | Medium | Medium | Blocking SDK work in thread pool; README production checklist documents the need for a queue/rate limiting before public scale |
| Dependency conflicts (fpdf vs fpdf2) | Low | Low | Pinned fpdf2; README troubleshooting entry with exact remediation command |

L = Likelihood, I = Impact.

# 8. Expected Deliverables

Runnable FastAPI application (app/ package) in demo + placeholder default mode.

Optional live integrations: Gemini two-stage text generation; Hugging Face hosted art; local Diffusers art.

Responsive web UI with preview, export and error pages.

Versioned JSON API with interactive documentation at /docs.

PDF export with cover page and per-panel pages.

UUID-based persistence with atomic manifests and a cleanup utility.

Automated pytest suite (11 tests) + ruff configuration.

Docker + compose packaging and OS-level setup/run scripts (Windows, macOS/Linux, Android).

Project documentation set (README, QUICKSTART, ANDROID-SPCK, PROJECT_ANALYSIS).

This 8-phase academic submission package, including diagrams, plans, tests, report, demonstration guide and viva material.

Companion file: The accompanying file Project_Gantt_Chart.xlsx contains the week-by-week schedule: a task table with planned dates and a colour-filled Gantt grid for weeks 1–8.